# Dandelion Master Plan — Weekly Priorities for Maximum Revenue Impact

Single consolidated plan: Website development · Revenue strategy · AI agents · Outbound sales

Last updated: July 26, 2026 (revised after [Consolidated Business Analysis](dandelion-consolidated-analysis.md))

Principle: Every week focuses on 2–3 high-impact moves — not everything at once.

# Data-Driven Mandate (Week 4 findings)

The [consolidated analysis](dandelion-consolidated-analysis.md) changes how weeks 5–12 are sequenced:

| Finding | Implication for this plan |
| --- | --- |
| ~$316K annualized — healthy revenue band | Don't chase more traffic first; fix ticket size and margin |
| Online is winning (49% share, +41% YTD, AOV $95–133) | Protect online recovery; deprioritize SEO/acquisition until POS + margin move |
| POS median AOV $49 — half of online | #1 lever — same designs, different counter pricing |
| Gross margin 31.5% (wholesale 63% of revenue) | #2 lever — stem-buy discipline, repricing heroes |
| Net ops 12–16% — overhead lean | Margin problem is COGS, not rent/labor overhead |
| Square email capture 7.4% | Retention blocked until identity captured at counter |
| Apr/Jun GP% 9–11% | Slow-month stem buys must flex with volume |

Operating rule (weeks 5–10): No new weddings, corporate, or SEO projects until POS median AOV ≥ $60 and monthly GP% ≥ 25% for two consecutive months.

Two focus metrics for the next 8 weeks:

POS median AOV: $49 → $75

Shop gross margin %: 31.5% → 38%

# How This Plan Is Prioritized

Work is ranked by expected revenue impact per hour invested, informed by measured baselines — not by task category.

| Priority tier | Definition | Examples |
| --- | --- | --- |
| P0 — Conversion leaks | Visitors or buyers are lost today | Homepage popup, duplicate products, broken checkout flow |
| P1 — AOV & margin | More revenue/profit per existing order | POS hero ladder, card upsell, stem-buy discipline, recost |
| P2 — Retention & LTV | Same customers buy again | Square email capture, win-back, occasion capture, subscriptions |
| P3 — Acquisition | New customers find you | SEO titles, Google Business, landing pages |
| P4 — High-LTV channels | Weddings, corporate, funeral homes | Forms, outbound, relationships |
| P5 — Scale & automate | Agents and systems reduce labor | Reminder agent, analyst agent, churn predictor |

Weekly time budget (recommended): 4–8 hours/week owner + optional 2–4 hours staff

Rule: Finish P1 (POS AOV + margin) before P4 (weddings/corporate). Online traffic is not the bottleneck.

# Target Metrics (Alameda-adjusted)

Track monthly via [2026 scorecard](strategy/monthly-scorecard-2026.csv) ([template](strategy/monthly-scorecard-template.csv)). Full write-up: [Consolidated Business Analysis](dandelion-consolidated-analysis.md) · [Revenue Baseline 2026 YTD](strategy/revenue-baseline-2026-ytd.md).

| Metric | Baseline (measured Jul 2026) | 90-day target | 12-month target |
| --- | --- | --- | --- |
| POS median AOV *(focus #1)* | $49 | $75 | $95+ |
| Gross margin % *(focus #2)* | 31.5% YTD (25.8% reclassified 2025) | 38%+ | 45% → 62% path |
| Blended AOV | Square mean $66; SS subtotal median $95 / total $121 | $90 | $110+ |
| Wholesale spend / revenue | 63% | <55% | <40% |
| Net ops margin | 12–16% (2023–25) | Maintain 12%+ | 12–14% |
| Repeat customer rate | Square 31%; SS email 21% (43% of 2026 SS orders from known emails) | 30%+ | 40%+ |
| Add-on attach (card) | 0.6% online (4/678 SS orders) | 20%+ | 30%+ |
| Active subscriptions | 4 SS sub orders in 2026 YTD (54 past sub-buyer emails) | 10 active | +20% YoY |
| Online channel share | 49% of bank deposits | Maintain 45–50% | — |
| Online YTD vs 2025 | Squarespace +41% through Jul 24 | Protect recovery | — |
| Email / phone capture (Square) | 7.4% of profiles | 70% of txs | 85%+ |
| Combined YTD (product-ish) | ~$185k (Square net $112k + SS subtotal $73k) | Track monthly | ~$316K annualized |
| Wedding inquiries → close | Under-tagged / not in SS | Track baseline | +2 weddings/quarter |

# What's Already Done (Don't Repeat)

| Item | Status |
| --- | --- |
| Sitemap loads | ✅ |
| Product page "HOW TO ORDER" copy | ✅ |
| Old checkout warning text removed | ✅ |
| Revenue exports uploaded + baseline analysis | ✅ Square + Squarespace + Stripe + accounts COGS → [baseline](strategy/revenue-baseline-2026-ytd.md) |
| Consolidated business analysis (accounts + revenue + customers) | ✅ [Consolidated report](dandelion-consolidated-analysis.md) · [Word](Dandelion_Consolidated_Analysis_Report.docx) |
| Product margin predictions (top 9 heroes) | ✅ [product-margin-analysis](strategy/product-margin-analysis.md) — all heroes below 38% GP |
| 90-day focus metrics chosen | ✅ POS AOV $49→$75 + GP% 31.5%→38% |

# 12-Week Roadmap at a Glance

| Week | Theme | Primary metrics moved | Est. hours | Status |
| --- | --- | --- | --- | --- |
| 1 | Stop revenue leaks | Conversion, trust | 4–6 | Partial |
| 2 | Raise online order value | Online AOV, card attach | 5–7 | Partial |
| 3 | Capture & retain buyers | Repeat rate, subs | 5–7 | ⬜ Open |
| 4 | Measure & recost | Margin, decisions | 3–5 | ✅ Analysis done |
| 5 | Fix POS AOV *(data #1)* | POS median AOV | 4–6 | ⬜ Next |
| 6 | Margin discipline *(data #2)* | GP%, wholesale % | 4–6 | ⬜ |
| 7 | Retention + identity capture | Repeat rate, email capture | 5–7 | ⬜ |
| 8 | Protect online recovery | Card attach, CRO fixes | 4–6 | ⬜ |
| 9 | Sympathy channel | Memorial revenue | 4–6 | ⬜ |
| 10 | Wedding pipeline | Wedding revenue | 5–8 | ⬜ |
| 11 | Corporate + holiday prep | B2B + seasonal | 6–10 | ⬜ |
| 12 | Review & replan | All KPIs | 2–4 | ⬜ |

Weeks 5–10 resequenced per [consolidated analysis](dandelion-consolidated-analysis.md): POS AOV and margin before weddings, corporate, and SEO.

# Week 1 — Stop Revenue Leaks (P0) 🟡 Partial

Goal: Fix what's actively costing orders and trust.

Carry-forward: Popup, duplicates, checkout fields, and test orders still open — complete in Week 8 alongside online CRO fixes.

## Website (Squarespace)

| Task | Impact | Time | Copy/assets |
| --- | --- | --- | --- |
| Remove homepage popup | P0 — blocks first-visit purchases | 30 min | [Week 1 guide](week-1-implementation-guide.md) |
| Delete duplicate products (Touch of Honey Copy, etc.) | P0 — trust + SEO | 45 min | [product-cleanup.csv](product-cleanup.csv) |
| Add gift message checkout field | P1 — experience + card upsell path | 20 min | Week 1 guide |
| Add occasion date capture at checkout | P2 — enables reminder agent later | 20 min | Optional field: "Recipient occasion date (for reminders)" |
| Verify pickup + local delivery settings | P0 — prevents cart abandonment | 30 min | Week 1 guide |
| Roll "HOW TO ORDER" copy to all arrangements (if not done) | P1 — reduces checkout confusion | 1 hr | [product-page-how-to-order.txt](copy/product-page-how-to-order.txt) |

## Revenue / data

| Task | Impact | Time |
| --- | --- | --- |
| ~~Export last 12 months orders/revenue~~ | ✅ Square + Squarespace + Stripe + accounts COGS | Done |
| ~~Upload to repo or share in chat~~ | ✅ See [`data/revenue/`](../data/revenue/) + analyses | Done |
| ~~Revenue Analyst review (AOV, channel, seasonality)~~ | ✅ [Week 4 analysis](strategy/revenue-customer-aov-analysis.md) | Done |
| Still need: active sub count + wedding tags + per-SKU recipe costs | Refines margin by product | 30–60 min |
| Run test order: delivery + pickup | P0 — verify flow | 30 min |

## AI / automation

| Task | Impact | Time |
| --- | --- | --- |
| Set up Wedding inquiry auto-acknowledge (email when form submitted) | P4 prep | 1 hr |

Week 1 success criteria:

☐  Popup gone

☐  No duplicate products on homepage

☐  Gift message + occasion fields live at checkout

☑  Revenue export uploaded (+ baseline written)

☐  Test orders pass

Est. revenue impact: Conversion recovery — industry suggests popups without CTAs cause 10–30% first-visit bounce; even 5 extra orders/week @ $90 = ~$23K/year.

# Week 2 — Raise Online Order Value (P1) 🟡 Partial

Goal: Increase online AOV and card attach. Online already hits $95+ median — focus on attach rate and premium anchors, not more traffic.

Carry-forward: Card upsell, SEO titles, post-delivery email — complete in Weeks 7–8.

## Website

| Task | Impact | Time | Assets |
| --- | --- | --- | --- |
| Card add-on prominent at checkout ($6.50) | P1 — AOV +$5–8 | 1 hr | Enable upsell block or post-cart prompt |
| Premium price anchoring on shop — show $180–310 next to $65–95 | P1 — lifts mid-tier | 45 min | Reorder product grid |
| Homepage + shop SEO titles | P3 — local search | 45 min | [seo-titles-and-meta.md](copy/seo-titles-and-meta.md) |
| Single homepage H1 — remove marquee H1 blocks | P3 — SEO + clarity | 1 hr | H1: "Flower Delivery in Alameda, Oakland & Berkeley" |
| Fix subscription typo (!2 → 12 Months) | P2 — sub trust | 15 min | Commerce → Products |

## Revenue

| Task | Impact | Time |
| --- | --- | --- |
| Recost top 5 SKUs (stems + labor + vessel) | P1 — margin | 2 hrs |
| Identify lowest-margin product | Pricing decision | 30 min |

## AI / automation

| Task | Impact | Time |
| --- | --- | --- |
| Launch Post-Delivery Growth email (thank-you + review link) | P2 — reviews + repeat | 2 hrs |
| Configure: no upsell on sympathy SKUs | Required | 15 min |

Week 2 success criteria:

☐  Card upsell live

☐  Shop page shows premium anchors

☐  SEO titles updated on Home + Shop

☐  Post-delivery email firing within 48 hrs of delivery

☐  Top 5 SKU costs documented

Est. revenue impact: +$8 AOV × 4,000 orders/year ≈ $32K revenue; reviews boost local SEO (indirect).

# Week 3 — Capture & Retain Buyers (P2) ⬜ Open

Goal: Turn one-time buyers into repeat customers. Prerequisite added: Square email/phone capture moves to Week 7 — retention is blocked at 7.4% capture today.

## Website

| Task | Impact | Time |
| --- | --- | --- |
| Subscription CTA on homepage (hero or banner) | P2 — sub LTV 3.4× | 1 hr |
| Memorial checkout fields (service date/time/location) | P4 — sympathy accuracy | 1 hr |
| Memorial + wedding pages: clear inquiry CTAs | P4 | 45 min |
| Google Business Profile: update hours, photos, services | P3 | 1 hr |

## Revenue

| Task | Impact | Time |
| --- | --- | --- |
| Email past 12-mo buyers: subscription offer | P2 | 1 hr |
| Define subscription referral incentive | P2 | 30 min |

## AI / automation

| Task | Impact | Time |
| --- | --- | --- |
| Checkout Upsell rules documented (sympathy = no upsell) | P1 | 30 min |
| Draft occasion reminder email templates (3) | P2 prep | 1 hr |

Week 3 success criteria:

☐  Subscription visible on homepage

☐  Memorial fields required on sympathy products

☐  Google Business updated

☐  One subscription campaign sent

Est. revenue impact: 2–5% of buyers → sub at $195/mo = $5–15K+ ARR from one campaign.

# Week 4 — Measure & Recost (Foundation) ✅ Analysis complete

Goal: Replace guesses with numbers. Set 90-day targets from real data.

## Revenue / analysis

| Task | Impact | Time |
| --- | --- | --- |
| Consolidated business analysis — accounts P&L + revenue + customers + benchmarks | ✅ [Done](dandelion-consolidated-analysis.md) | — |
| Complete [monthly scorecard](strategy/monthly-scorecard-2026.csv) | ✅ 2026 YTD filled with GP% | — |
| Compare actuals vs. [benchmarks](strategy/industry-benchmarks.md) | ✅ [Consolidated report](dandelion-consolidated-analysis.md) §3–4 | — |
| Choose 2 focus metrics for next 8 weeks | ✅ POS median AOV $49→$75 + GP% 31.5%→38% | — |
| Predicted margins for top 9 heroes | ✅ [product-margin-analysis](strategy/product-margin-analysis.md) — all below 38% GP | — |

## Still open (carry to Week 5–8)

| Task | Impact | Time | Week |
| --- | --- | --- | --- |
| [Week 1 QA checklist](checklists/week-1-qa.md) — full pass | Quality | 1 hr | Week 8 |
| Recipe-cost top 8 heroes (vs predicted margins) | Pricing decisions | 2–3 hrs | Week 6 |
| Active sub count + wedding tags in commerce data | CRM accuracy | 30–60 min | Week 7 |

Week 4 success criteria:

☑  Scorecard filled with real baseline (+ gross margin %)

☑  Consolidated analysis complete

☑  90-day targets written (2 metrics) — POS AOV + GP%

☑  Margin issues list created → [product-margin-analysis](strategy/product-margin-analysis.md)

☐  Week 1 website QA complete → Week 8

☐  Recipe costs for top 8 heroes → Week 6

Est. revenue impact: Indirect — prevents working on wrong levers. Resequencing weeks 5–10 to POS AOV + margin first is the highest-ROI decision from this week.

# Week 5 — Fix POS AOV (P1) ⬜ Next — Data lever #1

Goal: Close the $49 vs $95 gap. Same hero designs online and at the counter — different naming and pricing.

Why now: 40% of POS tickets are under $40. In-store median is half of online. This is the single largest revenue-per-hour lever (+$40–69K/yr at scale).

## Shop operations (OPS)

| Task | Impact | Time |
| --- | --- | --- |
| Map POS SKUs to online hero names (Touch of Honey, Love Poem, Moon, TLC, etc.) | P1 — enables ladder | 1 hr |
| Delete price-named SKUs ("20", "45 bouquet") from POS | P1 — stops under-asking | 30 min |
| Staff script: "Our most popular is Love Poem at $85 — would you like that or something larger?" | P1 — lifts median | 30 min |
| Train on hero ladder: entry $65–85 → mid $95–140 → premium $180–310 | P1 | 30 min |
| Track POS median AOV weekly in scorecard | P1 — accountability | 15 min/wk |

## Website (supporting)

| Task | Impact | Time |
| --- | --- | --- |
| Premium price anchoring on shop — show $180–310 next to $65–95 | P1 — lifts mid-tier online too | 45 min |
| Roll HOW TO ORDER to any remaining products | P1 | 30 min |

Week 5 success criteria:

☐  POS items renamed to match online hero catalog

☐  Price-named SKUs removed from POS

☐  Staff trained on upsell script

☐  POS median AOV ≥ $55 (interim checkpoint toward $75)

Est. revenue impact: Shifting half of ~1,000 sub-$60 tickets up $20 ≈ +$10–15K per similar YTD window; annualized +$40–69K.

# Week 6 — Margin Discipline (P1) ⬜ — Data lever #2

Goal: Move GP% from 31.5% toward 38%. Wholesale spend is 63% of revenue (benchmark: 28–35%). Apr/Jun hit 9–11% GP when stems don't flex.

Why now: 2025 was the warning year — revenue flat, wholesale up to 68%. Extra volume without margin discipline just buys more stems.

## Revenue / operations (OPS)

| Task | Impact | Time |
| --- | --- | --- |
| Recipe-cost top 8 heroes — compare to [predicted margins](strategy/product-margin-analysis.md) | P1 — pricing truth | 2–3 hrs |
| Raise Touch of Honey to $80–85 (worst GP at ~30%; volume leader) | P1 — +2–3 pts on mix | 30 min |
| Weekly stem-buy budget = forecasted orders × target COGS% (start at 62% GP target) | P1 — slow-month protection | 1 hr setup + 30 min/wk |
| Flag any SKU below 38% GP for price increase or retirement | P1 | 30 min |
| Reduce Jul/Aug stem orders to match seasonality (Jul avg GP% 14%) | P1 | 30 min |
| Separate sales tax from COGS in monthly tracking | P1 — benchmark accuracy | 30 min |

## Website

| Task | Impact | Time |
| --- | --- | --- |
| Update Commerce prices to match recost (heroes first) | P1 | 1 hr |

Week 6 success criteria:

☐  Top 8 heroes recipe-costed (actual vs predicted)

☐  Touch of Honey repriced

☐  Weekly stem-buy worksheet in use

☐  Monthly GP% ≥ 25% in current month (never below floor)

Est. revenue impact: COS flexing 5–10 pts in slow months = +$8–15K GP/yr; combined with Week 5 AOV lift → path to 38% GP.

# Week 7 — Retention + Identity Capture (P2) ⬜

Goal: Unlock the 5,986 SS payer emails and fix the 7.4% Square email capture rate. Retention is blocked without identity.

Why now: 43% of 2026 online orders already from returning emails — the list works when activated. But 40% of Square revenue is anonymous.

## Shop operations (OPS)

| Task | Impact | Time |
| --- | --- | --- |
| Require email or phone on every Square payment — staff process change | P2 — unlocks CRM | 30 min + daily habit |
| POS prompt: "Can I email you the receipt?" (default-on) | P2 | 15 min |

## Revenue / marketing

| Task | Impact | Time |
| --- | --- | --- |
| Win-back email to 2,745 occasional buyers ($100–299 lifetime spend) | P2 — largest pool | 1 hr |
| Sub offer to 54 past sub-buyers (only 4 sub orders YTD) | P2 — $23K ARR potential | 1 hr |
| Merge SS + Stripe email lists; dedupe | P2 | 1 hr |
| Tag active subscription count manually | P2 — baseline | 30 min |

## Website

| Task | Impact | Time |
| --- | --- | --- |
| Subscription CTA on homepage | P2 — sub LTV 3.4× | 1 hr |
| Memorial checkout fields (date/time/location) | P4 prep | 1 hr |
| Add "Send me reminders" opt-in at checkout | P2 | 30 min |

## AI / automation

| Task | Impact | Time |
| --- | --- | --- |
| Post-Delivery Growth email (thank-you + review link) | P2 | 2 hrs |
| Draft occasion reminder templates (3) | P2 prep | 1 hr |
| Occasion Reminder Agent — connect order export + email tool | P2 | 4–6 hrs |

Week 7 success criteria:

☐  Square email/phone capture ≥ 50% of txs (toward 70%)

☐  Win-back campaign sent to occasional tier

☐  Sub offer sent to 54 past buyers

☐  Post-delivery email firing within 48 hrs

☐  +5 new active subscriptions

Est. revenue impact: 8% reorder on occasional pool ≈ +$25–35K/yr at scale; 10 active subs @ $195/mo = $23K ARR.

# Week 8 — Protect Online Recovery (P1/P0) ⬜

Goal: Online is +41% YTD — don't lose it to conversion leaks. Complete Week 1 backlog + card attach.

Why now: Online share is 49% (at national benchmark). Card attach is 0.6% vs 30% target. Week 1 CRO items still open.

## Website (Squarespace) — Week 1 carry-forward

| Task | Impact | Time |
| --- | --- | --- |
| Remove homepage popup | P0 — blocks first-visit purchases | 30 min |
| Delete duplicate products (Touch of Honey Copy, etc.) | P0 — trust + SEO | 45 min |
| Card add-on prominent at checkout ($6.50, default-on if possible) | P1 — +$3–5K/yr | 1 hr |
| Gift message + occasion date fields at checkout | P1/P2 | 40 min |
| Verify pickup + local delivery settings | P0 | 30 min |
| Test delivery + pickup orders | P0 | 30 min |
| [Week 1 QA checklist](checklists/week-1-qa.md) — full pass | Quality | 1 hr |

## Website — Week 2 carry-forward

| Task | Impact | Time |
| --- | --- | --- |
| Homepage + shop SEO titles | P3 — deprioritized but quick | 45 min |
| Single homepage H1 (remove marquee blocks) | P3 | 1 hr |
| Fix subscription 12-month typo | P2 | 15 min |

## AI / automation

| Task | Impact | Time |
| --- | --- | --- |
| Configure: no upsell on sympathy SKUs | Required | 15 min |
| Review request link in post-delivery email | P2 | 15 min |

Week 8 success criteria:

☐  Popup gone; no duplicate products

☐  Card attach ≥ 10% (toward 20%)

☐  Test orders pass (delivery + pickup)

☐  Week 1 QA checklist complete

☐  Online YTD growth still positive vs 2025

Est. revenue impact: 25% card attach on 678 online orders ≈ +$3–5K/yr; conversion fixes protect the +41% recovery.

# Week 9 — Sympathy Channel (P4) ⬜

Goal: Grow a channel that's already material ($7K YTD, $139 AOV) and structurally fits Alameda (31.4% age 65+).

Gate: Only start if POS median AOV ≥ $60 and monthly GP% ≥ 25%.

## Website

| Task | Impact | Time |
| --- | --- | --- |
| Memorial page SEO title + meta | P3 | 30 min |
| Sympathy-specific landing copy (delivery windows, care) | P3 | 1 hr |
| Verify sympathy checkout validation works | P0 for channel | 30 min |
| Wedding + memorial inquiry CTAs | P4 | 45 min |

## AI / automation

| Task | Impact | Time |
| --- | --- | --- |
| Sympathy Order Intake Agent — internal alert if fields missing | P4 | 2 hrs |
| Compassionate post-delivery template (no upsell) | P2 | 30 min |

## Physical / outbound

| Task | Impact | Time |
| --- | --- | --- |
| Identify 5 Alameda/Oakland funeral homes | P4 | 1 hr |
| Prepare one-page sympathy menu PDF | P4 | 1 hr |
| Visit or email 2 funeral directors | P4 | 2 hrs |

Week 9 success criteria:

☐  Memorial SEO live

☐  2 funeral home contacts made

☐  Zero sympathy orders with missing service info

Est. revenue impact: 2–4 referral partners × 2–4 orders/mo × $139 AOV = $6–23K/year.

# Week 10 — Wedding Pipeline (P4) ⬜

Goal: Capture high-LTV wedding leads 24/7. Invoice channel already averages $165 — likely includes custom/wedding work.

Gate: Only start if Weeks 5–6 metrics are moving.

## Website

| Task | Impact | Time |
| --- | --- | --- |
| Wedding inquiry form (date, venue, guest count, budget, style) | P4 — $5.5–8K contracts | 2 hrs |
| Portfolio gallery refresh (best 12–20 images) | P4 — close rate | 2 hrs |
| Wedding page SEO title + meta | P3 | 30 min |

## AI / automation

| Task | Impact | Time |
| --- | --- | --- |
| Wedding Inquiry Triage Agent — auto-ack + lead score + draft reply | P4 | 3 hrs |
| Calendly/consultation link in auto-reply | P4 | 30 min |

## Physical (optional)

| Task | Impact | Time |
| --- | --- | --- |
| List 5 target venues; one outreach email each | P4 | 2 hrs |

Week 10 success criteria:

☐  Form live; auto-reply < 1 hour

☐  Portfolio updated

☐  5 venue/planner outreaches sent

☐  Wedding revenue tagged in commerce or spreadsheet

Est. revenue impact: +1–2 weddings/year = $6.5–16K.

# Week 11 — Corporate + Holiday Prep (P4/P1) ⬜

Goal: B2B pipeline for between-holiday revenue + Q4 seasonal readiness.

Adjust timing if Valentine's prep needs to start earlier (often Jan for florists).

## Physical / outbound — Corporate

| Task | Impact | Time |
| --- | --- | --- |
| Build list: 20 offices/hotels within 2 mi of Webster St | P4 | 2 hrs |
| Corporate Prospecting Agent — draft 10 personalized emails | P4 | 2 hrs |
| Send batch; schedule 3 follow-ups | P4 | 1 hr |
| 2 in-person visits | P4 | 2 hrs |

## Website — Holiday + Corporate

| Task | Impact | Time |
| --- | --- | --- |
| Simple "Office & Lobby Flowers" section or page | P4 | 1 hr |
| Holiday collection / gift guide page | P1 | 2 hrs |
| Premium anchors for Valentine's tier | P1 | 1 hr |
| Order cutoff dates prominent on homepage | P0 for holidays | 30 min |
| Corporate gifting page or PDF | P4 | 2 hrs |

## Marketing

| Task | Impact | Time |
| --- | --- | --- |
| Email: subscription as gift campaign | P2 | 1 hr |
| Corporate gifting outreach (10 accounts) | P4 | 2 hrs |
| Occasion reminders for Valentine's pre-booking | P2 | 1 hr |

Week 11 success criteria:

☐  10 corporate emails sent; 2 visits completed

☐  Holiday page live with cutoffs

☐  Corporate gift + sub gift campaigns sent

Est. revenue impact: 1 B2B account @ $200/week = $10.4K/yr; holiday prep protects Feb/May peaks (46% of YTD revenue).

# Week 12 — Review & Replan ⬜

Goal: Measure what worked against the Week 4 baseline. Set Q1 2027 priorities from data, not guesses.

| Task | Time |
| --- | --- |
| Fill [monthly scorecard](strategy/monthly-scorecard-2026.csv) for all 12 weeks | 1 hr |
| Compare to [Week 4 consolidated baseline](dandelion-consolidated-analysis.md) | 1 hr |
| Did POS median AOV reach $75? GP% reach 38%? | 30 min |
| What moved? What didn't? Retire low-ROI work | 30 min |
| Set Q1 2027 priorities (2 financial + 1 channel) | 1 hr |

Review questions:

POS median AOV: $49 → $___ (target $75)

Gross margin %: 31.5% → $___ (target 38%)

Wholesale % of revenue: 63% → $___ (target <55%)

Card attach: 0.6% → $___ (target 20%)

Square email capture: 7.4% → $___ (target 70%)

Active subscriptions: 4 → $___ (target 10)

# Work Type Legend (Every Task)

| Code | Meaning | Who |
| --- | --- | --- |
| WEB | Squarespace admin | Owner or VA |
| REV | Revenue/data/analysis | Owner |
| AI | Automation setup (Zapier, email, agents) | Owner + Cursor |
| OUT | Physical outbound / visits | Owner |
| OPS | Shop operations (recost, pricing) | Owner + designer |

# If You Only Have 4 Hours This Week

Do this, in order (data-prioritized as of Week 5):

Map POS SKUs to online hero names + delete price-named items (OPS — 1 hr) — biggest revenue lever

Remove homepage popup (WEB — 30 min) — protects +41% online recovery

Require email/phone on every Square payment (OPS — 30 min) — unlocks retention

Weekly stem-buy budget worksheet (OPS — 1 hr) — protects margin in slow months

Card upsell at checkout (WEB — 1 hr) — 0.6% → 20% attach = $3–5K/yr

These five items address POS AOV, margin, identity capture, online conversion, and card attach — the highest-ROI bundle from the consolidated analysis.

# Document Map (Consolidated)

| Topic | Document |
| --- | --- |
| This plan | `master-plan-weekly-priorities.md` |
| Business analysis (single source of truth) | [dandelion-consolidated-analysis.md](dandelion-consolidated-analysis.md) |
| Website task detail | [week-1-implementation-guide.md](week-1-implementation-guide.md) |
| Copy-paste assets | [copy/](copy/) |
| Revenue levers | [strategy/revenue-growth-framework.md](strategy/revenue-growth-framework.md) |
| Benchmarks & targets | [strategy/industry-benchmarks.md](strategy/industry-benchmarks.md) |
| Product margins | [strategy/product-margin-analysis.md](strategy/product-margin-analysis.md) |
| Physical vs digital | [strategy/physical-vs-digital-strategy.md](strategy/physical-vs-digital-strategy.md) |
| AI agents | [strategy/ai-agents-for-revenue.md](strategy/ai-agents-for-revenue.md) |
| Data intake | [strategy/revenue-data-intake.md](strategy/revenue-data-intake.md) |
| Weekly checklist | [checklists/weekly-execution-checklist.md](checklists/weekly-execution-checklist.md) |
| QA checklist | [checklists/week-1-qa.md](checklists/week-1-qa.md) |

# Quarterly View (After Week 12)

| Quarter | Focus | Key outcomes |
| --- | --- | --- |
| Q3 2026 (Weeks 1–6) | Fix leaks + POS AOV + margin | POS median → $60+, GP% → 35%+, baseline scorecard |
| Q4 2026 (Weeks 7–12) | Retention + protect online + high-LTV channels | Email capture 50%+, card attach 15%+, sympathy/wedding pipeline started |
| Q1 2027 | Corporate + margin path to 45% | 2+ B2B accounts, GP% 45%, wedding pipeline active |
| Q2 2027 | Acquisition + scale agents | Local SEO pages, full agent suite, GP% path to 62% |

Revisit quarterly — the consolidated analysis showed online traffic is not the bottleneck. If POS AOV and margin are moving by Week 8, accelerate sympathy/weddings. If not, stay on Weeks 5–6.